## Vulnerability Register
id | title | description | asset_id | asset_name | asset_owner | environment | business_impact | discovery_date | source | cvss_score | severity | status | remediation_owner | remediation_target_date | remediation_actual_date | remediation_plan | exception_id | risk_acceptance | verification_status | notes | related_tickets | standard_mapping
VULN-001 | Missing critical security patch on web server | WS-01 missing latest cumulative security update. | WS-01 | Public Web Server | Infrastructure Team | Production | Customer-facing outage / data exposure risk. | 2025-01-15 | Internal scan | 8.1 | High | Open | John Doe | 2025-01-25 |  | Apply patch during maintenance window. |  | No | Not Verified | Prioritise ahead of patch cycle. | CHG-12345 | ISO27001 A.8.8; CIS 7.1
VULN-002 | Weak TLS configuration | Legacy app supports TLS 1.0 and weak cipher suites. | APP-LEG-01 | Legacy App Server | App Team | UAT | Confidentiality/downgrade risk. | 2025-01-10 | Manual review | 5.6 | Medium | In Progress | Jane Smith | 2025-02-01 |  | Disable TLS 1.0/1.1 and weak ciphers; retest. | EXC-2025-001 | Temporary | Pending |  | CHG-12348 | ISO27001 A.8.24